## Milestones
Task ID | Title | Owner | Phase | Baseline date | Forecast date | Completed date | Status | Type | Slip (days) | Notes
M1 | Project kickoff | Project manager | Intake | 2026-11-02 | 2026-11-02 |  | Not started | Milestone
M2 | Business case approved | Business lead | Intake | 2026-11-16 | 2026-11-16 |  | Not started | Milestone
M3 | Gate: execution approval | IT lead | Preparation | 2026-12-21 | 2026-12-21 |  | Not started | Milestone
M4 | User acceptance testing complete | Project manager | Execution | 2027-03-02 | 2027-03-02 |  | Not started | Milestone
M5 | Go-live | Business lead | Handover | 2027-03-22 | 2027-03-22 |  | Not started | Milestone
M6 | Project closed | IT lead | Close | 2027-04-26 | 2027-04-26 |  | Not started | Milestone

## How to use
Milestone plan template with baseline and forecast
1. List your milestones, one per row. Task ID: any unique code, never change it.
2. Baseline date: the originally agreed date. Set it once and do not change it.
3. Forecast date: today's best estimate. Update it at every status meeting.
4. Slip (days) is calculated: forecast minus baseline. Positive = later than planned.
5. Status: Not started, In progress or Completed. Fill in the completed date when done.
6. Load the file into the free Project Health Check for a milestone timeline with baseline vs forecast:
https://ppmcompass.com/project-health-check/
Dates: dd.mm.yyyy. Your file is read in your browser and is not uploaded.
Template by PPM Compass. Free to use and adapt.