## Tasks
Task ID | Title | Owner | Bucket | Start date | Due date | Completed date | Status | Labels | Type
1 | Project kickoff | Project manager | Intake | 2026-11-02 | 2026-11-02 |  | Not started |  | Milestone
2 | Define scope and goals | Business lead | Intake | 2026-11-03 | 2026-11-12 |  | Not started |  | Task
3 | Business case approved | IT lead | Intake | 2026-11-16 | 2026-11-16 |  | Not started |  | Milestone
4 | Requirements workshop | Project manager | Preparation | 2026-11-17 | 2026-12-02 |  | Not started |  | Task
5 | Solution or vendor selection | Business lead | Preparation | 2026-11-22 | 2026-12-17 |  | Not started |  | Task
6 | Detailed project plan | IT lead | Preparation | 2026-12-02 | 2026-12-17 |  | Not started |  | Task
7 | Gate: execution approval | Project manager | Preparation | 2026-12-21 | 2026-12-21 |  | Not started |  | Milestone
8 | Build and configure | Business lead | Execution | 2026-12-22 | 2027-02-20 |  | Not started |  | Task
9 | Data migration | IT lead | Execution | 2027-01-11 | 2027-02-20 |  | Not started |  | Task
10 | Test preparation | Project manager | Execution | 2027-01-31 | 2027-02-25 |  | Not started |  | Task
11 | User acceptance testing complete | Business lead | Execution | 2027-03-02 | 2027-03-02 |  | Not started |  | Milestone
12 | End-user training | IT lead | Handover | 2027-03-03 | 2027-03-17 |  | Not started |  | Task
13 | Go-live | Project manager | Handover | 2027-03-22 | 2027-03-22 |  | Not started |  | Milestone
14 | Hypercare | Business lead | Handover | 2027-03-23 | 2027-04-11 |  | Not started |  | Task
15 | Lessons learned | IT lead | Close | 2027-04-12 | 2027-04-21 |  | Not started |  | Task
16 | Project closed | Project manager | Close | 2027-04-26 | 2027-04-26 |  | Not started |  | Milestone

## How to use
Project plan template with phases and milestones
1. Replace the example tasks with your own. Keep one row per task.
2. Task ID: any unique number or code. Keep it the same in every version of the file.
3. Bucket = phase (Intake, Preparation, Execution, Handover, Close). The timeline shows these as a phase band.
4. Type: write "Milestone" for milestones, "Task" for everything else.
5. Status: Not started, In progress or Completed. Fill in the completed date when a task is done.
6. Save a copy with the date in the file name every month (e.g. Project-plan-2026-11-01.xlsx).
7. Load two dated copies into the free Project Health Check to see delivery metrics and how each milestone moved:
https://ppmcompass.com/project-health-check/
Dates: dd.mm.yyyy. Your file is read in your browser and is not uploaded.
Template by PPM Compass. Free to use and adapt.